## Project Data
Project Name | Robot Visual Perception
Online team meeting | https://fau.zoom-x.de/j/62836031488
Production system (if any) | Service Provided (later in the Project)
Test system (if any) | Local Webcam
GitHub repository | https://github.com/amosproj/amos2025ws04-robot-visual-perception
GitHub feature board | https://github.com/orgs/amosproj/projects/92
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/95
Team T-shirt (white) | https://www.shirtinator.de/s/E_eIf-ElT4iidRVnqM8J5w
Team T-shirt (black) | https://www.shirtinator.de/s/R0CANDdWTRCOvCohq_encA
Additional materials | https://discord.gg/VDqD2Zfb
Team maling list | oss-amos-proj4@lists.fau.de
https://happy-amos.appspot.com/
Please use our mailing list for written communication. Only CC teachers (university) and coaches on specific topics, as the mailing lists are very long.

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Hilgers | Felix | fhilgers | felix.hilgers@fau.de
Samdani | Sarib | saribx | saribstudent@gmail.com
Chinbat | Anuun | anuunchin | anuun.ch@gmail.com
Goldschmidt | Georgina | bu31punu | dzsini.lost@gmail.com
Zinn | Benedikt | BenediktZinn | benedikt.wh.zinn@gmail.com
Badura | Emil | Tenebrae311 | badura@tu-berlin.de
Assenbaum | Paul | Paul2607 | paul.assenbaum@fau.de
Mantsch | Christoph | Christoph-Mantsch | christoph.cm.mantsch@fau.de
Asadi | Zohreh | zohrehasadi00 | z.asadi@campus.tu-berlin.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2025-10-22 | Felix Hilgers | Benedikt Zinn | Everyone else | Paul Assenbaum | Georgina Goldschmidt | (Tuesday 21. Discord for Release process example)
2 | 2025-10-29 | Benedikt Zinn | Felix Hilgers | Everyone else | Anuun Chinbat | Georgina Goldschmidt
3 | 2025-11-05 | Benedikt Zinn | Felix Hilgers | Everyone else | Sarib Samdani | Georgina Goldschmidt
4 | 2025-11-12 | Felix Hilgers | Benedikt Zinn | Everyone else | Sarib Samdani | Georgina Goldschmidt
5 | 2025-11-19 | Felix Hilgers | Benedikt Zinn | Everyone else | Anuun Chinbat | Georgina Goldschmidt
6 | 2025-11-26 | Benedikt Zinn | Felix Hilgers | Everyone else | Emil Badura | Georgina Goldschmidt
7 | 2025-12-03 | Felix Hilgers | Benedikt Zinn | Everyone else | Emil Badura | Georgina Goldschmidt
8 | 2025-12-10 | Benedikt Zinn | Felix Hilgers | Everyone else | Paul Assenbaum | Georgina Goldschmidt
9 | 2025-12-17 | Felix Hilgers | Benedikt Zinn | Everyone else | Christoph Mantsch | Georgina Goldschmidt
10 | 2026-01-07 | Benedikt Zinn | Felix Hilgers | Everyone else | Christoph Mantsch | Georgina Goldschmidt
11 | 2026-01-14 | Felix Hilgers | Benedikt Zinn | Everyone else | Zohreh Asadi | Georgina Goldschmidt
12 | 2026-01-21 | Benedikt Zinn | Felix Hilgers | Everyone else | Zohreh Asadi | Georgina Goldschmidt
13 | 2026-01-28 | Felix Hilgers | Benedikt Zinn | Everyone else |  | Georgina Goldschmidt
14 | 2026-02-04 | Benedikt Zinn | Felix Hilgers | Everyone else |  | Georgina Goldschmidt | Demo day!
15 | 2026-02-11 | Felix Hilgers | Benedikt Zinn | Everyone else | Anuun Chinbat | Georgina Goldschmidt | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Development of a visual perception system for robots with an accuracy of >= 90%
Meeting norms | Zoom-Meetings in the meeting room of the university. Joining the meeting is mandatory, with exceptions (like sickness, etc.). As an exception, showing up to 10 minutes late is fine if the team is informed via discord. Happiness Index: has to be completed at the end of the meeting (amos happy). Stand-up-mails: containing -> things done, problems encountered, things up next. -> For SDs: min 2x per week -> For POs: min 1x per week
Working norms | Issues on Github in the “Feature board” project of the repository. Definition of Done: If specified in the issue that the feature has to be tested, tests have to be written for that feature, documented (in code or later in the wiki) Git-branches: The latest commit on the main-branch has to be tagged. Only 2 “in progress” tickets per person at one time.
Coordination norms | Developers can create issues but not put them onto the “Feature board”. If blocked by a different task, discuss it as soon as possible. Communication should happen via Discord & mail. Criticism should be constructive. Language should be respectful at all times, both verbal and written communication.
Communication norms | Developers can create issues but not put them onto the “Feature board”. If blocked by a different task, discuss it as soon as possible. Communication should happen via Discord & mail. Criticism should be constructive. Language should be respectful at all times, both verbal and written communication.
Consideration norms
Cont. improvement norms
Rewards | Online coffee or lunch meet at some point.
Sanctions | Document absence. Repeated absence is addressed with the missing person directly but will later be escalated to professors.
Signatures
Scrum Master | Georgina Goldschmidt
Product owner | Felix Hilgers
Product owner | Benedikt Zinn
Software developer | Sarib Samdani
Software developer | Emil Badura
Software developer | Anuun Chinbat
Software developer | Paul Assenbaum
Software developer | Christoph Mantsch
Software developer | Zohreh Asadi

## Product Goal
Product Vision | Project Mission
Optibot helps people when operating robots equipped with a single camera. It gives real-time distance estimates for known objects inside the field of view of said camera without relying on other sensors. The software stack is easy to integrate with already existing WebRTC based systems, making it easy to enhance existing robot networks. | The mission of this project is to create a containerized system that processes a WebRTC stream as an input and outputs a stream of metadata. This metadata will contain the objects detected in a certain frame of the video stream, their bounding boxes in the image & the estimated distance. This information can be overlayed over the existing video stream in a React component. All components of the project have well definied interfaces and can easily be integrated into existing architectures.

## Product Glossary
Term | Definition
ONNX | Open Neural Network Exchange (A runtime to run machine learning models on a variety of hardware)
Monocular Depth Estimation | Estimating the Depth in a Scene with only one eye (or camera in our case)
YOLO | You Only Look Once, family of state of the art object detection models (and more)
MiDaS | A ML model for Monocular Depth Estimation
ML | Machine Learning
ORT | ONNX Runtime
CUDA | NVIDIA GPU runtime for machine learning and more
ROCm | AMD GPU runtime for machine learning and more
IoU | Intersection over Union
NMS | Non Maximum Suppression
FPS | Frames per Second
COCO | Common Objects in Context, a commonly used dataset for training and testing Object detection models
WebRTC | Web Real-Time Communication, video streaming between the different services
SBOM | Software Bill of Materials

## Sprint Goals
Sprint # | Sprint goal
1 | Meeting with industry partner and getting things started (and the T-shirt of course)
2 | Start work on individual components and research unclear topics
3 | Combining components into a first working prototype
4 | Refining prototype and splitting out components
5 | Finishing the Implementation of the Initial Architecture
6 | Refine component parts
7 | Improve Extensibility and Documentation
8 | Refining the overall look and feel
9 | Project integration with real SFU
10 | Technical Improvements and Experiments
11 | Refactoring and Testing
12 | Refining the Frontend
13 | Performance Improvements
14 | Finalizing the Documentation and Preparing for Demo Day
15 | Reflecting on the Project

## Velocity Tracking
Sprint # | Story Points Realized
1 | 0
2 | 14
3 | 22
4 | 11
5 | 21
6 | 26
7 | 24
8 | 19
9 | 19
10 | 23
11 | 11
12 | 12
13 | 0
14 | 0
15 | 0

## Velocity Chart
Average
18.3636
18.3636
18.3636
18.3636
18.3636
18.3636
18.3636
18.3636
18.3636
18.3636
18.3636
18.3636
18.3636
18.3636
18.3636

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 100 | 100
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 | Meeting with industry partner and getting things started (and the T-shirt of course) |  | 0 | 100 | 0 | 100
2 | Start work on individual components and research unclear topics |  | 16 | 100 | 14 | 100
3 | Combining components into a first working prototype |  | 21 | 84 | 22 | 86
4 | Refining prototype and splitting out components |  | 13 | 63 | 11 | 64
5 | Finishing the Implementation of the Initial Architecture |  | 25 | 50 | 21 | 53
6 | Refine component parts |  | 25 | 25 | 26 | 32
Features
1 | Meeting with industry partner and getting things started (and the T-shirt of course)
2 | Start work on individual components and research unclear topics
|  | Setup Architecture | 5 |  | 5
|  | Serve Webcam as WebRTC stream | 5 |  | 5
|  | Setup Initial CI Pipeline | 3 |  | 3
|  | Discuss Team Distribution Preferences | 3 |  | 1
3 | Combining components into a first working prototype
|  | Keep BOM up to date | 2 |  | 2
|  | Setup REUSE licensing | 2 |  | 3
|  | Update Architecture document | 2 |  | 2
|  | Create Object Detection Example | 3 |  | 3
|  | Prepare Build Process Review | 2 |  | 2
|  | Prepare Depth Estimation | 5 |  | 5
|  | Research Object and Depth Estimation | 5 |  | 5
4 | Refining prototype and splitting out components
|  | Metadata Transport | 5 |  | 3
|  | Split Backend Responsibilities | 3 |  | 3
|  | Improve Code Quality | 5 |  | 5
5 | Finishing the Implementation of the Initial Architecture
|  | Remove Redundant Calculations | 3 |  | 3
|  | Utilize Library for detecting Object dimensions | 5 |  | 5
|  | Create a React Video Component | 3 |  | 3
|  | Investigate and Fix startup TIme | 5 |  | 3
|  | Fix Windows Development setup | 3 |  | 3
|  | Create a React Video Overlay | 3 |  | 3
|  | Build Process Video | 1 |  | 1
|  | Update Container Images | 2 |  | 0
6 | Refine component parts
|  | Initialize Build/Deployment Documentation | 3 |  | 1
|  | Initialize Technical Documentation | 3 |  | 2
|  | Initialize User Facing Documentation | 3 |  | 3
|  | Setup and Test analyzing with Cuda and Rocm | 3 |  | 3
|  | Properly use CSS | 2 |  | 2
|  | Reduce Initial Connection Time | 2 |  | 2
|  | Automate SBOM Generation | 3 |  | 5
|  | Setup Docker Compose | 3 |  | 3
|  | Separate Model Downloading from Running | 3 |  | 5

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 156 | 156
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
7 | Improve Extensibility and Documentation |  | 22 | 156 | 24 | 156
8 | Refining the overall look and feel |  | 24 | 134 | 19 | 132
9 | Project integration with real SFU |  | 24 | 110 | 19 | 113
10 | Technical Improvements and Experiments |  | 22 | 86 | 23 | 94
11 | Refactoring and Testing |  | 13 | 64 | 11 | 71
12 | Refining the Frontend |  | 13 | 51 | 12 | 60
13 | Performance Improvements |  | 38 | 38 | 0 | 48
14 | Finalizing the Documentation and Preparing for Demo Day |  | 0 | 0 | 0 | 48
15 | Reflecting on the Project |  | 0 | 0 | 0 | 48
Features
7 | Improve Extensibility and Documentation
|  | Extensible Object Analysis | 3 |  | 2
|  | Send Object Location (x, y, z) relative to Camera | 3 |  | 5
|  | Move to pyproject.toml | 3 |  | 2
|  | Reduce Container Size | 3 |  | 1
|  | React Metadata Widget | 2 |  | 3
|  | Reduce Inference Time | 3 |  | 3
|  | Transported Metadata Usage | 5 |  | 8
8 | Refining the overall look and feel
|  | Ability to Hide Overlay | 1 |  | 0
|  | Debounce Detections in Metadata Widget | 3 |  | 3
|  | Add Support for Yolo11 | 2 |  | 1
|  | Create Make Targets for ONNX Export | 1 |  | 1
|  | Run MiDaS via ONNX | 2 |  | 2
|  | Overlay Flickering When Zoomed-in / -out | 3 |  | 2
|  | Clearing Overlay Unreliable | 2 |  | 2
|  | Overlay Drawn Out-of-bounds | 2 |  | 1
|  | Disconnecting Unreliable | 3 |  | 3
|  | Document Analyzer API Endpoints | 2 |  | 1
|  | Create Object Filter | 3 |  | 3
9 | Project integration with real SFU
|  | Smoother Overlays | 5 |  | 5
|  | Add Support for Depth Anything V2 | 3 |  | 2
|  | Standalone Model Downloading | 2 |  | 2
|  | Run on real Hardware | 2 |  | 2
|  | Video Stream from File | 3 |  | 3
|  | Backend Logging | 3 |  | 2
|  | Frontend Logging | 3 |  | 1
|  | Low Confidence Filter | 3 |  | 2
10 | Technical Improvements and Experiments
|  | Prometheus for Backend | 3 |  | 3
|  | Keep Metadata In Sync | 5 |  | 8
|  | Calibration Guide | 2 |  | 1
|  | Add Detection Threshold | 3 |  | 3
|  | Evalutate Apple Depth Pro | 2 |  | 2
|  | Label Mapping in Backend | 3 |  | 2
|  | Support multiple languages | 2 |  | 2
|  | Dark Light mode | 2 |  | 2
11 | Refactoring and Testing
|  | Improve depth estimation | 5 |  | 3
|  | UI Improvements | 3 |  | 5
|  | Overlay Frame Smoothing | 5 |  | 3
12 | Refining the Frontend
|  | Minor UI improvements | 2 |  | 2
|  | Centralized Configuration | 3 |  | 2
|  | Refactor & Test: Drawing Logic of frontend | 5 |  | 5
|  | Refactor & Test: Math functions | 3 |  | 3
13 | Performance Improvements
|  | Create Demo Day Slide | 2
|  | Create Demo Day Video | 5
|  | Refactor & Test: Object Tracking | 5
|  | Add Ion-Sfu Support | 3
|  | Video Router & Dispatching Service | 8
|  | Top Down Radar View | 5
|  | Restore Firefox support | 2
|  | Model quntization FP16 / INT8 | 3
|  | Tensor IO Binding | 3
|  | Align Model Inputs | 2
14 | Finalizing the Documentation and Preparing for Demo Day
Finalize User Facing Documentation
Finalize Design Documentation
Finalize Build Documentation
Update Architecture Diagrams
15 | Reflecting on the Project
Create Project Report
99 | Out of Scope
Optimize Preprocessing
Optimize Postprocessing

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done
| Code has been reviewed by at least one SD | All Software Components are functioning | Architecture documentation has been updated
| Feature has been reviewed by at least one PO | Sprint release notes have been generated from all merge-requests since the last release | Tests exist for all mayor features
| Build scripts have been adapted if necessary | All container communication is working | All tests are passing
CI Pipeline Passes
Code has been merged to main
BOM has been updated if necessary

## Documentation
Type | Link / reference

## Bill of Materials
# | Context | Name | Version | License
1 | Frontend (React UI) | npm:react | 18.3.1 | MIT
2 | Frontend (React UI) | npm:react-dom | 18.3.1 | MIT
3 | Backend (FastAPI API) | pypi:aioice | 0.10.1 | BSD-3-Clause
4 | Backend (FastAPI API) | pypi:aiortc | 1.14.0 | BSD-3-Clause
5 | Backend (FastAPI API) | pypi:av | 16.0.1 | BSD-3-Clause
6 | Backend (FastAPI API) | pypi:fastapi | 0.115.10 | MIT
7 | Backend (FastAPI API) | pypi:httpx | 0.27.2 | BSD License
8 | Backend (FastAPI API) | pypi:numpy | 1.26.4 | BSD-3-Clause
9 | Backend (FastAPI API) | pypi:onnxruntime | 1.20.1 | MIT License
10 | Backend (FastAPI API) | pypi:onnxruntime | 1.20.1 | MIT License
11 | Backend (FastAPI API) | pypi:onnxruntime-gpu | 1.23.2 | MIT License
12 | Backend (FastAPI API) | pypi:opencv-python | 4.9.0.80 | Apache 2.0
13 | Backend (FastAPI API) | pypi:opentelemetry-exporter-otlp | 1.27.0 | Apache-2.0
14 | Backend (FastAPI API) | pypi:opentelemetry-sdk | 1.27.0 | Apache-2.0
15 | Backend (FastAPI API) | pypi:opentelemetry-semantic-conventions | 0.48 | Apache-2.0
16 | Backend (FastAPI API) | pypi:prometheus-client | 0.21.0 | Apache Software License 2.0
17 | Backend (FastAPI API) | pypi:pydantic | 2.12.3 | MIT License
18 | Backend (FastAPI API) | pypi:timm | 1.0.22 | Apache-2.0
19 | Backend (FastAPI API) | pypi:transformers | 4.49.0 | Apache 2.0 License
20 | Backend (FastAPI API) | pypi:ultralytics | 8.3.58 | AGPL-3.0
21 | Backend (FastAPI API) | pypi:uvicorn | 0.38.0 | BSD-3-Clause
22 | Backend (FastAPI API) | pypi:websockets | 15.0.1 | BSD-3-Clause
23 | Frontend (React UI) | npm:@types/react | 18.3.12 | MIT
24 | Frontend (React UI) | npm:@types/react-dom | 18.3.1 | MIT
25 | Frontend (React UI) | npm:@typescript-eslint/eslint-plugin | 8.16.0 | MIT
26 | Frontend (React UI) | npm:@typescript-eslint/parser | 8.16.0 | BSD-2-Clause
27 | Frontend (React UI) | npm:@vitejs/plugin-react | 4.3.4 | MIT
28 | Frontend (React UI) | npm:autoprefixer | 10.4.22 | MIT
29 | Frontend (React UI) | npm:eslint | 9.17.0 | MIT
30 | Backend Dev Dependencies | pypi:mypy | 1.13.0 | MIT
31 | Backend Dev Dependencies | pypi:onnx | 1.19.1 | Apache License v2.0
32 | Backend Dev Dependencies | pypi:onnxscript | 0.5.6 | MIT
33 | Backend Dev Dependencies | pypi:onnxslim | 0.1.75 | MIT
34 | Frontend (React UI) | npm:postcss | 8.5.6 | MIT
35 | Frontend (React UI) | npm:prettier | 3.4.2 | MIT
36 | Backend Dev Dependencies | pypi:pytest | 8.3.3 | MIT
37 | Backend Dev Dependencies | pypi:pytest-asyncio | 1.2.0 | Apache License v2.0
38 | Backend Dev Dependencies | pypi:reuse | 4.0.3 | Apache-2.0 AND CC0-1.0 AND CC-BY-SA-4.0 AND GPL-3.0-or-later
39 | Backend Dev Dependencies | pypi:ruff | 0.7.0 | MIT
40 | Frontend (React UI) | npm:tailwindcss | 3.4.16 | MIT
41 | Frontend (React UI) | npm:typescript | 5.6.3 | Apache-2.0
42 | Frontend (React UI) | npm:vite | 6.0.3 | MIT
43 | Frontend (React UI) | npm:vitest | 2.1.5 | MIT

## Planning Poker
Last Name | First Name | Value
|  |  | 3 | OK
Samdani | Sarib | 3
Chinbat | Anuun | 3
Badura | Emil | 3
Assenbaum | Paul |  | 0 | No size
Mantsch | Christoph |  | 1 | Trivial size
Asadi | Zohreh | 3 | 2 | Small size
|  |  | 3 | Medium size
Hilgers | Felix |  | 5 | Large size
Goldschmidt | Georgina |  | 8 | Very large size
Zinn | Benedikt |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value