## Project Data
Project Name | Robot Visual Perception
Online team meeting | https://fau.zoom-x.de/j/62836031488
Production system (if any) | Service Provided (later in the Project)
Test system (if any) | Local Webcam
GitHub repository | https://github.com/amosproj/amos2025ws04-robot-visual-perception
GitHub feature board | https://github.com/orgs/amosproj/projects/92
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/95
Team T-shirt (white) | https://www.shirtinator.de/s/E_eIf-ElT4iidRVnqM8J5w
Team T-shirt (black) | https://www.shirtinator.de/s/R0CANDdWTRCOvCohq_encA
Additional materials | https://discord.gg/VDqD2Zfb
Team maling list | oss-amos-proj4@lists.fau.de
https://happy-amos.appspot.com/
Please use our mailing list for written communication. Only CC teachers (university) and coaches on specific topics, as the mailing lists are very long.

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Hilgers | Felix | fhilgers | felix.hilgers@fau.de
Samdani | Sarib | saribx | saribstudent@gmail.com
Chinbat | Anuun | anuunchin | anuun.ch@gmail.com
Goldschmidt | Georgina | bu31punu | dzsini.lost@gmail.com
Zinn | Benedikt | BenediktZinn | benedikt.wh.zinn@gmail.com
Badura | Emil | Tenebrae311 | badura@tu-berlin.de
Assenbaum | Paul | Paul2607 | paul.assenbaum@fau.de
Mantsch | Christoph | Christoph-Mantsch | christoph.cm.mantsch@fau.de
Asadi | Zohreh | zohrehasadi00 | z.asadi@campus.tu-berlin.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2025-10-22 | Felix Hilgers | Benedikt Zinn | Everyone else | Paul Assenbaum | Georgina Goldschmidt | (Tuesday 21. Discord for Release process example)
2 |  | Benedikt Zinn | Felix Hilgers | Everyone else | Anuun Chinbat | Georgina Goldschmidt
3 |  | Benedikt Zinn | Felix Hilgers | Everyone else | Sarib Samdani | Georgina Goldschmidt
4 |  | Felix Hilgers | Benedikt Zinn | Everyone else | Sarib Samdani | Georgina Goldschmidt
5 |  | Felix Hilgers | Benedikt Zinn | Everyone else | Anuun Chinbat | Georgina Goldschmidt
6 |  | Benedikt Zinn | Felix Hilgers | Everyone else | Emil Badura | Georgina Goldschmidt
7 |  | Felix Hilgers | Benedikt Zinn | Everyone else | Emil Badura | Georgina Goldschmidt | Mid-term due
8 |  | Benedikt Zinn | Felix Hilgers | Everyone else | Paul Assenbaum | Georgina Goldschmidt
9 |  | Felix Hilgers | Benedikt Zinn | Everyone else | Christoph Mantsch | Georgina Goldschmidt
10 | 2023-01-11 | Benedikt Zinn | Felix Hilgers | Everyone else | Christoph Mantsch | Georgina Goldschmidt
11 |  | Felix Hilgers | Benedikt Zinn | Everyone else | Zohreh Asadi | Georgina Goldschmidt
12 |  | Benedikt Zinn | Felix Hilgers | Everyone else | Zohreh Asadi | Georgina Goldschmidt
13 |  | Felix Hilgers | Benedikt Zinn | Everyone else |  | Georgina Goldschmidt
14 |  | Benedikt Zinn | Felix Hilgers | Everyone else |  | Georgina Goldschmidt | Demo day!
15 |  | Felix Hilgers | Benedikt Zinn | Everyone else |  | Georgina Goldschmidt | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here

## Team Contract
Goals | Development of a visual perception system for robots with an accuracy of >= 90%
Meeting norms | Zoom-Meetings in the meeting room of the university. Joining the meeting is mandatory, with exceptions (like sickness, etc.). As an exception, showing up to 10 minutes late is fine if the team is informed via discord. Happiness Index: has to be completed at the end of the meeting (amos happy). Stand-up-mails: containing -> things done, problems encountered, things up next. -> For SDs: min 2x per week -> For POs: min 1x per week
Working norms | Issues on Github in the “Feature board” project of the repository. Definition of Done: If specified in the issue that the feature has to be tested, tests have to be written for that feature, documented (in code or later in the wiki) Git-branches: The latest commit on the main-branch has to be tagged. Only 2 “in progress” tickets per person at one time.
Coordination norms | Developers can create issues but not put them onto the “Feature board”. If blocked by a different task, discuss it as soon as possible. Communication should happen via Discord & mail. Criticism should be constructive. Language should be respectful at all times, both verbal and written communication.
Communication norms | Developers can create issues but not put them onto the “Feature board”. If blocked by a different task, discuss it as soon as possible. Communication should happen via Discord & mail. Criticism should be constructive. Language should be respectful at all times, both verbal and written communication.
Consideration norms
Cont. improvement norms
Rewards | Online coffee or lunch meet at some point.
Sanctions | Document absence. Repeated absence is addressed with the missing person directly but will later be escalated to professors.
Signatures
Scrum Master | Georgina Goldschmidt
Product owner | Felix Hilgers
Product owner | Benedikt Zinn
Software developer | Sarib Samdani
Software developer | Emil Badura
Software developer | Anuun Chinbat
Software developer | Paul Assenbaum
Software developer | Christoph Mantsch
Software developer | Zohreh Asadi

## Product Goal
Product Vision | Project Mission
Optibot helps people when operating robots equipped with a single camera. It gives real-time distance estimates for known objects inside the field of view of said camera without relying on other sensors. The software stack is easy to integrate with already existing WebRTC based systems, making it easy to enhance existing robot networks. | The mission of this project is to create a containerized system that processes a WebRTC stream as an input and outputs a stream of metadata. This metadata will contain the objects detected in a certain frame of the video stream, their bounding boxes in the image & the estimated distance. This information can be overlayed over the existing video stream in a React component. All components of the project have well definied interfaces and can easily be integrated into existing architectures.

## Product Glossary
Term | Definition

## Sprint Goals
Sprint # | Sprint goal
1 | Meeting with industry partner and getting things started (and the T-shirt of course)
Start work on individual components and research unclear topics
Combining components into a first working prototype
Refining prototype and splitting out components
Finishing the Implementation of the Initial Architecture

## Velocity Tracking
Sprint # | Story Points Realized
1 | 0

## Velocity Chart
Average

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
Features
|  | Setup Architecture | 5 |  | 5
|  | Serve Webcam as WebRTC stream | 5 |  | 5
|  | Setup Initial CI Pipeline | 3 |  | 3
|  | Discuss Team Distribution Preferences | 3 |  | 1
|  | Keep BOM up to date | 2 |  | 2
|  | Setup REUSE licensing | 2 |  | 3
|  | Update Architecture document | 2 |  | 2
|  | Create Object Detection Example | 3 |  | 3
|  | Prepare Build Process Review | 2 |  | 2
|  | Prepare Depth Estimation | 5 |  | 5
|  | Research Object and Depth Estimation | 5 |  | 5
|  | Metadata Transport | 5 |  | 3
|  | Split Backend Responsibilities | 3 |  | 3
|  | Improve Code Quality | 5 |  | 5
|  | Remove Redundant Calculations | 3
|  | Automate SBOM Generation | 3
|  | Utilize Library for detecting Object dimensions | 5
|  | Create a React Video Component | 3
|  | Investigate and Fix startup TIme | 5
|  | Fix Windows Development setup | 3
|  | Create a React Video Overlay | 3
|  | Build Process Video | 1
|  | Setup Docker Compose | 3
|  | Update Container Images | 2
|  | Use Metadata in the Frontend for Drawing the Overlay | 5
|  | Create Initial Video Router / Dispatching Service | 8
|  | Separate Model Downloading from Running | 3

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1
...
Features
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done
| Code has been reviewed by at least one SD | All Software Components are functioning | Architecture documentation has been updated
| Feature has been reviewed by at least one PO | Sprint release notes have been generated from all merge-requests since the last release | Tests exist for all mayor features
| Build scripts have been adapted if necessary | All container communication is working | All tests are passing
CI Pipeline Passes
Code has been merged to main
BOM has been updated if necessary

## Documentation
Type | Link / reference

## Planning Poker
Value
3
3
|  | 21 | 0 | No size
|  |  | 1 | Trivial size
|  |  | 2 | Small size
Asadi | Zohreh | 3 | 3 | Medium size
|  |  | 5 | Large size
|  |  | 8 | Very large size
| Benedikt |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value
no cap yet

## Bill of Materials
# | Context | Name | Version | License | Comment
1 | Frontend (React UI) | npm:react | 18.3.1 | MIT
2 | Frontend (React UI) | npm:react-dom | 18.3.1 | MIT
3 | Backend (FastAPI API) | pypi:aioice | 0.10.1 | BSD-3-Clause
4 | Backend (FastAPI API) | pypi:aiortc | 1.14.0 | BSD-3-Clause
5 | Backend (FastAPI API) | pypi:av | 16.0.1 | BSD-3-Clause
6 | Backend (FastAPI API) | pypi:fastapi | 0.115.10 | MIT
7 | Backend (FastAPI API) | pypi:httpx | 0.27.2 | BSD License
8 | Backend (FastAPI API) | pypi:numpy | 1.26.4 | BSD-3-Clause
9 | Backend (FastAPI API) | pypi:opencv-python | 4.9.0.80 | Apache 2.0
10 | Backend (FastAPI API) | pypi:pydantic | 2.12.3 | MIT
11 | Backend (FastAPI API) | pypi:timm | 1.0.22 | Apache-2.0
12 | Backend (FastAPI API) | pypi:ultralytics | 8.3.58 | AGPL-3.0
13 | Backend (FastAPI API) | pypi:uvicorn | 0.38.0 | BSD-3-Clause
14 | Frontend (React UI) | npm:@types/react | 18.3.12 | MIT
15 | Frontend (React UI) | npm:@types/react-dom | 18.3.1 | MIT
16 | Frontend (React UI) | npm:@typescript-eslint/eslint-plugin | 8.16.0 | MIT
17 | Frontend (React UI) | npm:@typescript-eslint/parser | 8.16.0 | BSD-2-Clause
18 | Frontend (React UI) | npm:@vitejs/plugin-react | 4.3.4 | MIT
19 | Frontend (React UI) | npm:eslint | 9.17.0 | MIT
20 | Backend Dev Dependencies | pypi:mypy | 1.13.0 | MIT
21 | Frontend (React UI) | npm:prettier | 3.4.2 | MIT
22 | Backend Dev Dependencies | pypi:pytest | 8.3.3 | MIT
23 | Backend Dev Dependencies | pypi:pytest-asyncio | 1.2.0 | Apache-2.0
24 | Backend Dev Dependencies | pypi:reuse | 4.0.3 | Apache-2.0 AND CC0-1.0 AND CC-BY-SA-4.0 AND GPL-3.0-or-later
25 | Backend Dev Dependencies | pypi:ruff | 0.7.0 | MIT
26 | Frontend (React UI) | npm:typescript | 5.6.3 | Apache-2.0
27 | Frontend (React UI) | npm:vite | 6.0.3 | MIT
28 | Frontend (React UI) | npm:vitest | 2.1.5 | MIT