## Project Data
Project Name | Robot Visual Perception
Online team meeting | https://fau.zoom-x.de/j/62836031488
Production system (if any) | Service Provided (later in the Project)
Test system (if any) | Local Webkit
GitHub repository | https://github.com/amosproj/amos2025ws04-robot-visual-perception
GitHub feature board | https://github.com/orgs/amosproj/projects/92
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/95
Team T-shirt (white) | https://www.shirtinator.de/s/E_eIf-ElT4iidRVnqM8J5w
Team T-shirt (black) | https://www.shirtinator.de/s/R0CANDdWTRCOvCohq_encA
Additional materials | https://discord.gg/VDqD2Zfb
Team maling list | oss-amos-proj4@lists.fau.de
https://happy-amos.appspot.com/
Please use our mailing list for written communication. Only CC teachers (university) and coaches on specific topics, as the mailing lists are very long.

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Hilgers | Felix | fhilgers | felix.hilgers@fau.de
Khan | Muhamad | mukahn | md.kahn@tu-berlin.de
Samdani | Sarib | saribx | saribstudent@gmail.com
Chinbat | Anuun | anuunchin | anuun.ch@gmail.com
Goldschmidt | Georgina | bu31punu | dzsini.lost@gmail.com
Zinn | Benedikt | BenediktZinn | benedikt.wh.zinn@gmail.com
Badura | Emil | Tenebrae311 | badura@tu-berlin.de
Assenbaum | Paul | Paul2607 | paul.assenbaum@fau.de
Mantsch | Christoph | Christoph-Mantsch | christoph.cm.mantsch@fau.de
Asadi | Zohreh | zohrehasadi00 | z.asadi@campus.tu-berlin.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2025-10-22 | Felix Hilgers | Benedikt Zinn | Everyone else | Paul Assenbaum | Georgina Goldschmidt | (Tuesday 21. Discord for Release process example)
2 | 2025-10-29 | Benedikt Zinn | Felix Hilgers | Everyone else | Anuun Chinbat | Georgina Goldschmidt
3 | 2025-11-05 | Felix Hilgers | Benedikt Zinn | Everyone else | Sarib Samdani | Georgina Goldschmidt
4 | 2025-11-12 | Benedikt Zinn | Felix Hilgers | Everyone else | Sarib Samdani | Georgina Goldschmidt
5 | 2025-11-19 | Felix Hilgers | Benedikt Zinn | Everyone else | Anuun Chinbat | Georgina Goldschmidt
6 | 2025-11-26 | Benedikt Zinn | Felix Hilgers | Everyone else | Emil Badura | Georgina Goldschmidt
7 | 2025-12-03 | Felix Hilgers | Benedikt Zinn | Everyone else | Emil Badura | Georgina Goldschmidt | Mid-term due
8 | 2025-12-10 | Benedikt Zinn | Felix Hilgers | Everyone else | Paul Assenbaum | Georgina Goldschmidt
9 | 2025-12-17 | Felix Hilgers | Benedikt Zinn | Everyone else | Christoph Mantsch | Georgina Goldschmidt
10 | 2023-01-11 | Benedikt Zinn | Felix Hilgers | Everyone else | Christoph Mantsch | Georgina Goldschmidt
11 | 2023-01-18 | Felix Hilgers | Benedikt Zinn | Everyone else | Zohreh Asadi | Georgina Goldschmidt
12 | 2023-01-25 | Benedikt Zinn | Felix Hilgers | Everyone else | Zohreh Asadi | Georgina Goldschmidt
13 | 2023-02-01 | Felix Hilgers | Benedikt Zinn | Everyone else |  | Georgina Goldschmidt
14 | 2023-02-08 | Benedikt Zinn | Felix Hilgers | Everyone else |  | Georgina Goldschmidt | Demo day!
15 | 2023-02-15 | Felix Hilgers | Benedikt Zinn | Everyone else |  | Georgina Goldschmidt | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Development of a visual perception system for robots with an accuracy of >= 90%
Meeting norms | Zoom-Meetings in the meeting room of the university. Joining the meeting is mandatory, with exceptions (like sickness, etc.). As an exception, showing up to 10 minutes late is fine if the team is informed via discord. Happiness Index: has to be completed at the end of the meeting (amos happy). Stand-up-mails: containing -> things done, problems encountered, things up next. -> For SDs: min 2x per week -> For POs: min 1x per week
Working norms | Issues on Github in the “Feature board” project of the repository. Definition of Done: If specified in the issue that the feature has to be tested, tests have to be written for that feature, documented (in code or later in the wiki) Git-branches: The latest commit on the main-branch has to be tagged. Only 2 “in progress” tickets per person at one time.
Coordination norms | Developers can create issues but not put them onto the “Feature board”. If blocked by a different task, discuss it as soon as possible. Communication should happen via Discord & mail. Criticism should be constructive. Language should be respectful at all times, both verbal and written communication.
Communication norms | Developers can create issues but not put them onto the “Feature board”. If blocked by a different task, discuss it as soon as possible. Communication should happen via Discord & mail. Criticism should be constructive. Language should be respectful at all times, both verbal and written communication.
Consideration norms
Cont. improvement norms
Rewards | Online coffee or lunch meet at some point.
Sanctions | Document absence. Repeated absence is addressed with the missing person directly but will later be escalated to professors.
Signatures
Scrum Master | Georgina Goldschmidt
Product owner | Felix Hilgers
Product owner | Benedikt Zinn
Software developer | Sarib Samdani
Software developer | Emil Badura
Software developer | Anuun Chinbat
Software developer | Paul Assenbaum
Software developer | Christoph Mantsch
Software developer | Zohreh Asadi

## Product Goal
Product Vision | Project Mission
The reason of existence of the envisioned product (beyond this project). | The mission of this particular project (in the context of the product vision).

## Product Glossary
Term | Definition

## Sprint Goals
Sprint # | Sprint goal
1 | Meeting with industry partner and getting things started (and the T-shirt of course)
2 | Start work on individual components and research unclear topics
3 | Combining components into a first working prototype
4 | Refining prototype and splitting out components
5
6
7
8
9
10
11
12
13
14
15

## Velocity Tracking
Sprint # | Story Points Realized
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done

## Documentation
Type | Link / reference

## Bill of Materials
# | Context | Name | Version | License | Comment | Status | Change Info
1 | Frontend (React UI) | npm:react | 18.3.1 | MIT | UI framework | In Use
2 | Frontend (React UI) | npm:react-dom | 18.3.1 | MIT | DOM renderer for React | In Use
3 | Frontend (React UI) | npm:typescript | 5.6.3 | Apache-2.0 | Type system for JavaScript | In Use | Version updated: 5.4.5 → 5.6.3
4 | Frontend (React UI) | npm:vite | 6.0.3 | MIT | Build tool and dev server | In Use | Version updated: 5.2.0 → 6.0.3
5 | Frontend (React UI) | npm:websocket | 1.0.35 | MIT | WebSocket client for metadata | Planned
6 | Frontend (React UI) | npm:webrtc-adapter | 9.1.2 | BSD-3-Clause | Cross-browser WebRTC compatibility | Planned
7 | Frontend (React UI) | npm:axios | 1.7.2 | MIT | HTTP client for REST API | Planned
8 | Frontend (React UI) | npm: zustand | 4.5.3 | MIT | State management | Planned
9 | Frontend (React UI) | npm:three | 0.169.0 | MIT | for 3D-visualization | Planned (optional)
10 | Frontend (React UI) | npm:@types/react | 18.3.12 | MIT | TypeScript definitions for React | In Use | New component
11 | Frontend (React UI) | npm:@types/react-dom | 18.3.1 | MIT | TypeScript definitions for React DOM | In Use | New component
12 | Frontend (React UI) | npm:@vitejs/plugin-react | 4.3.4 | MIT | Vite plugin for React support | In Use | New component
13 | Frontend (React UI) | npm:eslint | 9.17.0 | MIT | Code linting | In Use | New component
14 | Frontend (React UI) | npm:prettier | 3.4.2 | MIT | Code formatting | In Use | New component
15 | Frontend (React UI) | npm:vitest | 2.1.5 | MIT | Unit testing framework | In Use | New component
16 | Frontend (React UI) | npm:@typescript-eslint/eslint-plugin | 8.16.0 | MIT | ESLint rules for TypeScript | In Use | New component
17 | Frontend (React UI) | npm:@typescript-eslint/parser | 8.16.0 | MIT | TypeScript parser for ESLint | In Use | New component
18 | Backend (FastAPI API) | pypi:uvicorn | 0.38.0 | BSD-3-Clause | ASGI server for FastAPI | In Use | Version updated: 0.30.1 → 0.38.0
19 | Backend (FastAPI API) | pypi:fastapi | 0.115.10 | MIT | Web framework for API | In Use | Version updated: 0.115.2 → 0.115.10
20 | Backend (FastAPI API) | pypi:websockets | 13.1 | BSD-3-Clause | WebSocket server for real-time metadata | Planned (optional)
21 | Backend (FastAPI API) | pypi:grpcio | 1.66.1 | Apache-2.0 | gRPC for AI service communication | Planned (optional)
22 | Backend (FastAPI API) | pypi:httpx | 0.27.0 | BSD-3-Clause | Async HTTP client | Planned
23 | Backend (FastAPI API) | pypi:pydantic | 2.12.3 | MIT | Data validation for FastAPI | In Use | New component
24 | Backend (FastAPI API) | pypi:aiortc | 1.14.0 | BSD-3-Clause | Python WebRTC implementation | In Use | New component
25 | Backend (FastAPI API) | pypi:av | 16.0.1 | BSD-2-Clause | Audio/Video processing for aiortc | In Use | New component
26 | Backend (FastAPI API) | pypi:ruff | 0.7.0 | MIT | Fast Python linter | In Use | New component
27 | Backend (FastAPI API) | pypi:pytest | 8.3.3 | MIT | Testing framework | In Use | New component
28 | Backend (FastAPI API) | pypi:mypy | 1.13.0 | MIT | Static type checker | In Use | New component
29 | WebRTC Signaling | go:pion/webrtc | 3.2.35 | MIT | Go WebRTC library for signaling service | Planned (optional)
30 | WebRTC Signaling | go:gorilla/websocket | 1.5.2 | BSD-2-Clause | WebSocket library for Go | Planned (optional)
31 | Image Analysis (Python) | pypi:opencv-python | 4.9.0.80 | Apache-2.0 | Computer vision library | In Use | Version updated: 4.10.0.84 → 4.12.0.88
32 | Image Analysis (Python) | pypi:numpy | 1.26.4 | BSD-3-Clause | Numerical operations | In Use | Version updated: 2.1.1 → 2.2.6
33 | Image Analysis (Python) | pypi:torch | 2.3.1 | BSD-3-Clause | PyTorch ML framework | Planned
34 | Image Analysis (Python) | pypi:torchvision | 0.18.1 | BSD-3-Clause | Computer vision models for PyTorch | Planned
35 | Image Analysis (Python) | pypi:midas | 3.1 | MIT | for depth recognition | Planned
36 | Image Analysis (Python) | pypi:ultralytics | 8.2.14 | APGL-3.0 | for computer vision | Planned
37 | Infrastructure/Deployment | docker:python | 3.11-slim | PSF | Base container for Python services | Planned
38 | Infrastructure/Deployment | docker:golang | 20-alpine | MIT | Base container for Go service | Planned
39 | Infrastructure/Deployment | docker:nvidia/cuda | 12.4.1-base | NVIDIA Software License | GPU acceleration for AI inference | Planned (optional)
40 | Infrastructure/Deployment | helm:kubernetes | 1.13.0 | Apache-2.0 | Container orchestration | Planned (optional)
41 | Infrastructure/Deployment | prometheus/prometheus | 2.54.0 | Apache-2.0 | Monitoring and metrics | Planned (optional)
42 | Infrastructure/Deployment | grafana/grafana | 11.1.0 | AGPL-3.0 | Visualization dashboards | Planned

## Planning Poker
Last Name | First Name | Value
Hilgers | Felix |  | #DIV/0! | #DIV/0!
Samdani | Sarib
Chinbat | Anuun
Goldschmidt | Georgina |  | 0 | No size
Zinn | Benedikt |  | 1 | Trivial size
Badura | Emil |  | 2 | Small size
Assenbaum | Paul |  | 3 | Medium size
Mantsch | Christoph |  | 5 | Large size
Asadi | Zohreh |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value
no cap yet